## Sheet1
Project: [Project Name] | Bug ID | Task ID | Date Reported | Reported by | Assigned to: [Developer/Tester - Optional] | Status | Priority: | Severity | Component | Summary: [Concise description of the bug] | Description
| BUG-001 | API-TC-31 | 2024-12-25 | Yesitha | Jeewantha Kodikara | Open | HIgh | Critical | API | Expected : "204 No Content" Actual : "403 Forbidden" | Precondition : The admin user is logged into the system. The book to be deleted already exists in the system and is accessible to the admin. Expected result : The book should be successfully deleted. The API should return 204) The book should no longer exist in the system. Actual Result : Received Status Code: 403 Forbidden
| BUG-002 | API-TC-34 | 2024-12-26 | Yesitha | Jeewantha Kodikara | New | HIgh | Critical | API | Expected : 403 Forbidden Actual : 200 OK | Precondition : Admin/user has created a book and the user is logged in with username and password Expected result : The API should return a 403 status code indicating that the user is not authorized to delete the book. Actual Result : The API returned a 200 status code, allowing the user to delete the book.
| BUG-003 | API-TC-35 | 2024-12-27 | Yesitha | Jeewantha Kodikara | Open | Medium | Major | API | Expected : 403 Forbidden Actual : 405 Method not Allowed | Precondition : Ensure the application is running and accessible.User logged in Expected result : The API should return a 403 status code indicating forbidden access as a user is not allowed to delete Actual Result : The API returned a 405 Method Not Allowed status code
| BUG-004 | API-TC-36 | 2024-12-30 | Yesitha | Jeewantha Kodikara | In progress | HIgh | Critical | API | Expected : 403 Forbidden Actual : 404 Not Found | Precondition : Ensure the application is running and accessible.User logged in Expected result : The API should return a 403 status code indicating forbidden access for users Actual Result : The API returned a 404 status code
| BUG-005 | API-TC-17 | 2025-01-01 | Piyumanthi | Jeewantha Kodikara | New | HIgh | Critical | API | Expected : 200 Success code Actual : 403 Forbidden | Precondition : Admin has created a book with a valid ID. The user is authenticated and logged in Expected result : The system should return the book's details, including its ID, title, author. The API should return 200 Actual Result : The API returned a 403 status code
| BUG-006 | API-TC-18 | 2025-01-02 | Piyumanthi | Jeewantha Kodikara | Open | HIgh | Critical | API | Expected :404 status code. Actual : 403 Forbidden | Precondition : User is authenticated and logged in. The bookId is either non-numeric, empty, or refers to a book that does not exist in the system If the book does not exist in the system., Expected result : Should return a 404 Not Found error with the error message "Book not found" Actual Result : Returned a 403 status code - User is not permitted
| BUG-007 | API-TC-21 | 2024-12-27 | Prasadi | Jeewantha Kodikara | In progress | Low | Minor | API | Expected : 401 Unauthorized Actual : 403 Forbidden | Precondition : Ensure the application is running and accessible at http://localhost:7081. Admin has created a book. The user is logged in with a user role Expected result : The API should return a 401 Unauthorized error, indicating that the user does not have permission to update the book. Actual Result : The API returned a 403 Forbidden error .
| BUG-008 | API-TC-27 | 2024-01-31 | Anudhi | Jeewantha Kodikara | Open | Medium | Major | API | Expected : 400 Bad Request Actual : 208 Already Reported | Precondition : There should be at least one book in the system. Expected result : Status Code: 400 "Bad Request" due to missing author Actual Result : Status Code: 208 "Already Reported"
| BUG-009 | API-TC-05 | 2025-01-03 | Kalana | Jeewantha Kodikara | Open | Low | Major | API | Expected result : Created ID should be equal with CustomId Actual Result : Created ID was not equal to CustomId | Precondition : Admin should be logged in Admin gives a POST request with a CustomID Expected result : Created ID should be equal with CustomId Actual Result : Created ID was not equal to CustomId
| BUG-010 | API-TC-08 | 2025-01-03 | Kalana | Jeewantha Kodikara | Open | HIgh | Critical | API | Expected : 400 Bad Request Actual :201 Created | Precondition : Admin should be logged in Expected result : The system should return a 400 Bad Request error due to no title and author parameters, with message - Mandatory parameters should not be null Actual Result : The actual result was a 201 Created status instead of the expected 400 Bad Request
| BUG-011 | API-TC-09 | 2025-01-03 | Kalana | Jeewantha Kodikara | Open | Medium | Major | API | Expected : 400 Bad Request Actual : 208 Already Reported | Precondition : Admin should be logged in Expected result : The system should return a 400 Bad Request error due to no title parameter, with message - Mandatory parameters should not be null Actual Result : Received a 208 Already Reported status code - with message " Book exists already"
| BUG-012 | API-TC-10 | 2025-01-03 | Kalana | Jeewantha Kodikara | Open | Medium | Major | API | Expected : 400 Bad Request Actual : 208 Already Reported" | Precondition : Admin should be logged in Expected result : The system should return a 400 Bad Request error due to missing title, with message - Mandatory parameters should not be null Actual Result : Received a 208 Already Reported status code - with message " Book exists already"
| BUG-013 | API-TC-11 | 2025-01-03 | Kalana | Jeewantha Kodikara | Open | Medium | Major | API | Expected : 400 Bad Request Actual : 208 Already Reported | Precondition : Admin should be logged in Expected result : The system should return a 400 Bad Request error due to empty title. Actual Result : Received a 208 Already Reported status code - with message " Book exists already"
| BUG-014 | API-TC-32 | 2024-12-30 | Yesitha | Jeewantha Kodikara | Open | Low | Minor | API | Expected : 400 Bad Request Actual : 405 Method Not Allowed | Precondition : The admin user is logged into the system. The API endpoint for deleting books requires a valid book ID as part of the request URL. Expected result : Status Code: 400 Bad Request due to missing book ID Actual Result : Received Status Code: 405 Method Not Allowed
| BUG-015 | API-TC-33 | 2024-12-30 | Yesitha | Jeewantha Kodikara | New | HIgh | Critical | API | Expected : 404 Not Found Actual : 403 Forbidden | Precondition : Admin is logged in and the application is running Expected result : Should return a 404 status code indicating "Book Not Found." Actual Result :Returned a 403 status code